## Sheet1
Use Case | SOM Status | BPM Status | Priority | Description | Additional Notes
L2S2101 | Completed | Pending | 1 | Create customer (Residential)
L2S2103 - L2S2108 | Completed | Pending | 1 | Update Customer Category
L2S2104 | Completed | Pending | 1 | Update Customer Address
L2S2105 | Completed | Pending | 1 | Update Payment Arrangment of a customer
L2S2106 | New | New | 1 | Update contract address
L2S2113 | New | New |  | Add Customer to Directory Inquiry
L2S2114 | New | New |  | Remove Customer from Directory Inquiry
S2C2101 | N/A | N/A |  | Open custome from CTI
S2C2102 | Completed | Pending | 1 | Customer read (reading status, balance and customer code)
S2C2103 | New | New | 1 | Get Customer contracts (should be done for all LOBs)
S2C2105 | New | New |  | Get contract details
S2C2111 | New | New | 1 | Get customer Invoices
S2C2112 | New | New |  | View Customer Debit/Credit Notes from Customer Care | Check with Ali Younes where this case should be implemented
S2C2113 - L2S3101 | New | New | 1 | Get Customer payments
S2C2118 - S2C2121 | New | New |  | Get Invoice Details
S2C2122 | New | New |  | Request Call Details Statement from Customer Care
S2C2126 | New | New | 1 | Bill on demand
S2C2130 | Completed | New | 1 | Cancel Invoice Installment
S2C2133 | New | New |  | Service history details
S2C2136 | Completed | New | 1 | Get Installment Templates
E2R2101 - E2R2102 | New | New |  | Bill Dispute (invoice complaint)
L2S3103 - L2S3104 - L2S3107 | New | New |  | Cash and Invoice Payments in payment step | 103 and 107 are not aligned with the HLD, these use cases need discussions before implementation
L2S3112 | Completed | Completed | 1 | Get All rate plans
L2S3113 | Completed | New | 1 | Get allowed services on a rate plan
L2S3116 - L2S3119 | New | New | 1 | Create contract on hold and Billing Account | We will do it for telephony
L2S3128 | New | New |  | Get Resources Request in PBX creation
L2S3143 - L2S3146 - L2S3153 - S2C3121 | New | New | 1 | ADSL, GHADSL and Leased Line Contract Activation | Same call in SOM for all contract activations of all LOBs
L2S3154 | New | New |  | Add contract to professional Directory Inquiry
L2S3155 | New | New |  | Remove contract from profressional Directory Inquiry
L2S3201 | New | New |  | Service addition on a contract
S2C3112 | New | N/A |  | Contract Soft Suspension from Dunning
S2C3112 | New | N/A |  | Contract Suspension from dunning
S2C3114 | New | N/A |  | Contract deactivation from dunning
S2C3115 | New | N/A |  | Revoke Contract soft suspension from dunning
S2C3116 | New | N/A |  | Revoke Contract suspension from dunning
S2C3117 | New | New |  | Contract suspension from CRM
S2C3119 | New | New |  | Activate Pabx service
S2C3120 | New | New |  | Activate CPT service
S2C3123 | New | New |  | Change Rate Plan
S2C3124 | New | New |  | Alter ADSL Speed
S2C3125 | New | New |  | Deactivate wireline contract from CRM | Don’t have an idea about it and it should be included in other requests
S2C3128 | New | New |  | Request Directory Number Change from Customer Care | Postman
S2C3138 | New | New |  | Micro cells | No idea about it
S2C3139 | New | New |  | Change Phone Number Order
S2C3140 | New | New |  | Contract Take Over
S2C3144 | New | New |  | Line Move
S2C3145 | New | New |  | ADSL Line Move Different Switch
S2C3146 | New | New |  | Line Move Different Switch
S2C3150 | New | New |  | Block Customer from CRM | Postman
S2C3151 | New | New |  | Unblock customer from CRM | Postman
S2C3154 | New | New |  | Fulfill Services Add Order for xDSL | No idea about it, it should be handled before
S2C3156 | New | New |  | Fuflill Services Add Order for Telephony | No idea about it, it should be handled before