## Sheet2
Auto Num | Task Name | % Complete (CRM Side) | % Complete (Over ALL) | Can Be Viewed | Required Man days for completion | Notes
Contact Center
1 | BPM-CCR-001 : Contact Types | 100% | 100% | Yes | 0
2 | BPM-CCR-002 : Account Types | 100% | 80% | Yes | 1
3 | BPM-CCR-003 : Create Retail Syrian Customer | 80% | 80% | Yes | 2
4 | BPM-CCR-004 : Create Retail Non-Syrian Customer | 80% | 80% | Yes | 1
5 | BPM-CCR-005 : Create Official Customer | 50% | 50% | Yes | 1
6 | BPM-CCR-006 : Create Enterprise Customer | 50% | 50% | Yes | 1
7 | BPM-CCR-008 : Contacts Mapping to Customer Groups | 100% | 20% | Yes
8 | BPM-CCR-009 : Validate Existing Customer | 100% | 100% | Yes
9 | BPM-CCR-010 : Reading Customer Status | 100% | 20% | Yes
10 | BPM-CCR-011 : Blacklisted Customer | 70% | 100% | Yes | 1 | Forbidden logic
11 | BPM-CCR-012 : Blacklisted Customer Restrictions | 20% | 20% | Yes | 2 | Black Listed, balance and advantagous
12 | BPM-CCR-013 : Updating Customer Information | 100% | 0% | Yes |  | Needs calls to BSCS in order to update Address or any other data
13 | BPM-CCR-014 : Change Payment Method | 100% | 0% | Yes |  | Needs a call on BSCS
14 | BPM-CCR-015 : Customer File Display | 0% | 0% | NO
15 | BPM-CCR-016 : Enable IVR Usage | 100% | 100% | Yes
16 | BPM-CCR-017 : Set IVR Password | 90% | 100% | Yes | 0.1 | need to add a button
17 | BPM-CCR-018 : Set Selfcare Password | 90% | 100% | Yes | 0.1 | need to add a button
18 | BPM-CCR-019 : Setting Directory Inquiry Option | 100% | 100% | Yes | 0.1
19 | BPM-CCR-022 : Check Order Status | 0% | 0% | Yes | 2 | Needs work on SOM and then show result as a detail grid on CRM whenever needed
20 | BPM-CCR-023 : Identify Calling Customer | 35% | 35% | NO | 5
21 | BPM-CCR-024 : Customer Care Workflow Definition |  |  | Yes
22 | BPM-CCR-025 : Customer Search | 50% |  | Yes | 0.1 | Fixed filters
23 | BPM-CCR-026 : Contract Search | 0% | 0% | No | 1 | Page to search for contracts, a grid showing all contracts of all types
24 | BPM-CCR-027 : Order Search | 0% |  | NO | 2 | Search for operations (use the request table)
25 | BPM-CCR-028 : Auditing Customer Information Updates | 0% |  | NO | 2
26 | BPM-CCR-029 : CRM Users |  |  | Yes
27 | BPM-CCR-030 : Contact Sub-types |  |  | Yes
28 | BPM-CCR-031 : Activate service through call centre | 100% | 0% | NO |  | Filtering services per CSO
Customer Assurance
29 | BPM-CAS-001 : Generate Documents Based on Template | 30% |  | Yes | 1 | We need the documents to implement them
30 | BPM-CAS-002 : Attach Documents | 100% |  | Yes
31 | BPM-CAS-003 : Register Technical Complaint | 0% |  | NO | 3
32 | BPM-CAS-004 : Register Administrative Complaint | 0% |  | NO | 3
33 | BPM-CAS-005 : Close Technical Complaint |  |  | No
34 | BPM-CAS-006 : Close Administrative Complaint |  |  | NO
35 | BPM-CAS-007 : ISP registered complaints |  |  | NO
36 | BPM-CAS-008 : Complaint delay cause | 0% |  | NO | N/A | Escalation Process
37 | BPM-CAS-009 : Supervise delayed cases | 0% |  | NO | N/A
38 | BPM-CAS-010 : Business line subscription templates process | 0% |  | NO | N/A | 45 days on hold in a specific step, release the request and do a specific opertion
39 | BPM-CAS-011 : Services request templates process |  |  | NO
40 | BPM-CAS-012 : Administrative complaint template process |  |  | NO
Customer Information Management
41 | BPM-CIM-001 : Contracts Type | 80% |  | Yes | N/A | missing ISDN PRI
42 | BPM-CIM-003 : Retrieve PSTN/ISDN Technical Line Description | 100% |  | Yes
43 | BPM-CIM-004 : Retrieve WCDMA Technical Line Description | 0% |  | Yes | 1
44 | BPM-CIM-005 : Retrieve PES Technical Line Description | 100% |  | Yes
45 | BPM-CIM-006 : DP Port on Multiplexer | 100% |  | Yes
46 | BPM-CIM-008 : Telephony Line Reservation Options | 100% |  | Yes
47 | BPM-CIM-009 : Get Free PSTN Telephony Line | 100% |  | Yes
48 | BPM-CIM-010 : Get Free PES Telephony Line | 100% |  | Yes
49 | BPM-CIM-011 : Get Free ISDN Telephony Line | 100% |  | Yes
50 | BPM-CIM-012 : Get Free WCDMA Telephony Line | 100% |  | Yes
51 | BPM-CIM-013 : Get Free DID Telephony Line | 0% |  | Yes | 3
52 | BPM-CIM-014 : Get Free Leased Line | 100% |  | Yes
53 | BPM-CIM-015 : xDSL Line Reservation Options | - |  | No
54 | BPM-CIM-016 : Get Free ADSL Line | 80% |  | Yes | 0.5
55 | BPM-CIM-017 : Get Free GSHDSL Line | 0% |  | NO | 3 | with termination
56 | BPM-CIM-018 : Get Free DP Ports | - |  | Yes
57 | BPM-CIM-019 : Get Free WCDMA Receiver Ports | - |  | No
58 | BPM-CIM-020 : Get Free Phone Numbers | 100% |  | Yes
59 | BPM-CIM-021 : Line Description Document | 90% |  | Yes | 0.1 | Button print if reserve = false
60 | BPM-CIM-022 : Deposit Payment for Waiting List Option | 0% |  | NO | 0.3
61 | BPM-CIM-023 : Add to Waiting List Feature | 100% |  | Yes
62 | BPM-CIM-024 : Remove Prospect from Waiting List | 100% |  | Yes
63 | BPM-CIM-025 : Reserve Line Path | 80% |  | Yes | 0.3 | Requires changes from Nabil's side
64 | BPM-CIM-026 : Rate Plan Selection | 70% |  | Yes | 2 | To define the catalog and read from it
65 | BPM-CIM-027 : Services Selection | 100% |  | Yes
66 | BPM-CIM-028 : Check Service Parameters | 100% |  | Yes
67 | BPM-CIM-029 : Check Services Consistency | 100% |  | NO
68 | BPM-CIM-030 : Check Services Availability | 0% |  | NO | 0.2
69 | BPM-CIM-031 : Evaluate Subscription Fees | 100% |  | NO
70 | BPM-CIM-032 : Fees Payment Method | 100% |  | Yes
71 | BPM-CIM-033 : Insurance Deposit Amount | 100% |  | NO
72 | BPM-CIM-034 : Create Telephony Contract Order | 100% |  | Yes
73 | BPM-CIM-035 : Submit Activate Contract Order | 100% |  | Yes
74 | BPM-CIM-036 : Create PBX Line Service | 100% |  | NO
75 | BPM-CIM-037 : PBX Line Service Adding | 100% |  | NO
76 | BPM-CIM-038 : PBX Line Service Deletion | 100% |  | NO
77 | BPM-CIM-039 : Supported Telephony Line Operations | 100% |  | Yes
78 | BPM-CIM-040 : Supported Leased Line Operations | 100% |  | NO |  | last mile change missing from XAkTA
79 | BPM-CIM-041 : Supported ADSL Line Customer requests | 100% |  | NO
80 | BPM-CIM-042 : Supported Fibre Operations |  |  | NO
81 | BPM-CIM-043 : Restricting Line Actions |  |  | No | 0.2 | operation validation
82 | BPM-CIM-044 : Restricting Telephony Line Operations |  |  | NO | 0.2 | operation validation
83 | BPM-CIM-045 : Advantageous Scenarios |  |  | NO | 0.2 | operation validation
84 | BPM-CIM-046 : Check Customer Service Registry | - |  | NO
85 | BPM-CIM-047 : Submit Activate Service Order | 0% |  | Yes | 0.5
86 | BPM-CIM-048 : Submit Deactivate Service Order | 0% |  | Yes | 0.5 | wait for E/// descision (make it from grid or dropdown)
87 | BPM-CIM-049 : Submit Line Blocking Order | 100% |  | Yes
88 | BPM-CIM-050 : Submit Line Unblocking Order | 100% |  | Yes
| BPM-CIM-052 : Submit Bill on Demand Order |  |  | NO
89 | BPM-CIM-053 : Request Call Details | 100% |  | NO
90 | BPM-CIM-054 : Submit Change Rate Plan Order | 100% |  | NO
91 | BPM-CIM-055 : Submit Change Phone Number Order | 90% |  | Yes | 0.2 | add change rate plan in case PSTN to ISDN or vice versa
92 | BPM-CIM-056 : Submit Contract Takeover Order | 100% |  | NO
93 | BPM-CIM-057 : Line Moving in same Switch | 100% |  | Yes
94 | BPM-CIM-058 : Submit Deport Number Order | 100% |  | NO
95 | BPM-CIM-059 : Friends and Family Management | 0% |  | NO | 2
96 | BPM-CIM-060 : ADSL subscription add to waiting list | 100% |  | NO
97 | BPM-CIM-061 : ADSL Alter Speed | 100% |  | NO
98 | BPM-CIM-062 : ADSL Alter Speed Fee | 100% |  | NO
99 | BPM-CIM-063 : Switch tagged under waiting list | 100% |  | NO
100 | BPM-CIM-064 : ADSL Print Reservation Document | 100% |  | NO
101 | BPM-CIM-065 : Professional services | - |  | NO |  | related to Directory Inquiry
102 | BPM-CIM-066 : Open Balance Check Exceptions | 0% |  | NO | 0.2 | operation validation
| BPM-CIM-067 : ADSL contract takeover |  |  | NO
103 | BPM-CIM-068 : ADSL Change Password | 100% |  | NO
104 | BPM-CIM-069 : ADSL change port | 0% |  | NO |  | part of technical complaints
105 | BPM-CIM-070 : Directory Inquiry | 0% | 0% | NO
106 | BPM-CIM-071 : Directory Inquiry GUI | 0% | 0% | NO
107 | BPM-CIM-072 : Resume subscription from waiting list | 100% |  | Yes
108 | BPM-CIM-073 : Define payment responsible for Accounts | 0% |  | NO | 1 | checkbox + validation
109 | BPM-CIM-074 : Prove contact sub-type | 100% |  | Yes
110 | BPM-CIM-075 : Set ADSL username | 100% |  | NO
111 | BPM-CIM-076 : Cancel contract creation |  |  | NO | N/A | 45 days on hold in a specific step, release the request and do a specific opertion
112 | BPM-CIM-077 : Add CPT Service | 100% |  | NO
113 | BPM-CIM-078 : Remove CPT Service | 100% |  | NO
114 | BPM-CIM-079 : Submit Add CPT Service Order | 100% |  | NO
115 | BPM-CIM-080 : Submit Remove CPT Service Order | 100% |  | NO
116 | BPM-CIM-081 : Leased Line Moving | 0% |  | NO | 1 | discuss with nabil
117 | BPM-CIM-082 : Line Moving To New Switch | 100% |  | NO
118 | BPM-CIM-083 : Change customer password for network services | 100% |  | NO
119 | BPM-CIM-084 : Override telephony subscriptions threshold due to free phone numbers count limit on switch | - |  | NO |  | check with nabil
120 | BPM-CIM-085 : Create ADSL Contract | 100% |  | NO
121 | BPM-CIM-086 : Create GSHDSL Contract | 0% |  | NO | 2
122 | BPM-CIM-087 : Create Leased Line Contract | 70% |  | Yes | 0.5 | XAKTA: get microwave equipments
123 | BPM-CIM-088 : Create FTTB contract |  |  | NO
124 | BPM-CIM-089 : Contract Deactivation | 80% |  | Yes | 0.5 | missing GSHDSL termination
125 | BPM-CIM-090 : OCC Addition by Accounting team | 80% |  | NO | 0.2 | user must be in accounting team (group)
126 | BPM-CIM-091 : Bulk Operations | - |  | NO |  | Postponed by Ali
127 | BPM-CIM-092 : Move ADSL contract line port | 100% |  | NO
128 | BPM-CIM-093 : ADSL ISP ordering | 100% |  | NO
129 | BPM-CIM-094 : Add Service Operation | 100% |  | Yes
130 | BPM-CIM-095 : Billing Account Creation | 100% |  | Yes |  | added by email to update contract address make it as operation on all contracts
Identity Management
131 | BPM-IDM-001 : Customer Care User Access Rights | 100% |  | NO
Information Management
132 | BPM-IFM-001 : Internal admin notifications |  |  | Yes
Resource Management and Control
133 | BPM-RMC-001 : Manage Phone number to Device connectivity | 100% |  | Yes
134 | BPM-SRA-002 : Change Device Command | 100 |  | Yes
Core Billing and Invoice
135 | BPM-CBI-001 : Initiate Instalment Request | 0 |  | NO | 1
136 | BPM-CBI-002 : Select Instalment Plan | 0 |  | NO | 1
137 | BPM-CBI-003 : Instalment Plan Payment Calculations | 0 |  | NO | 1
138 | BPM-CBI-004 : Instalment Plan Payment Reductions | 0 |  | NO | 1
139 | BPM-CBI-005 : Instalment Plan Approval | 0 |  | NO | 1