## Progress
Progress | 42.3077
Total WS | 52
Completed | 17
Partial Complete | 5
Pending | 1
New | 29

## BSCS WS UC
Use Case | SOM Status | Priority | Description | Vanrise Notes | Original Assigned Date | New Planned Date | Delay (days) | Related Issues(ID on bug Tracker)
L2S2101 | Completed | 1 | Create customer (Residential) |  | 2019-04-12
L2S2103 - L2S2108 | Completed | 1 | Update Customer Category |  | 2019-04-12
L2S2104 | Completed | 1 | Update Customer Address |  | 2019-04-12
L2S2105 | Completed | 1 | Update Payment Arrangment of a customer |  | 2019-04-12
L2S2106 | Completed | 1 | Update contract address |  | 2019-04-12
L2S2113 | Completed | 3 | Add Customer to Directory Inquiry |  | 2019-04-23
L2S2114 | Completed | 3 | Remove Customer from Directory Inquiry |  | 2019-04-23
S2C2101 | N/A | 3 | Open custome from CTI
S2C2102 | Completed | 1 | Customer read (reading status, balance and customer code) |  | 2019-04-12
S2C2103 | Partialy Completed | 1 | Get Customer contracts (should be done for all LOBs) |  | 2019-04-12 |  |  | #25
S2C2105 | Partialy Completed | 2 | Get contract details |  | 2019-04-18 |  | 1 | #24 #27
S2C2111 | Completed | 1 | Get customer Invoices |  | 2019-04-12
S2C2112 | Completed | 3 | View Customer Debit/Credit Notes from Customer Care |  | 2019-04-24
S2C2113 - L2S3101 | Completed | 1 | Get Customer payments |  | 2019-04-12
S2C2118 - S2C2121 | Blocked | 3 | Get Invoice Details | We are not able to get generated invocies, please check issue #43 on bug tracker for more details | 2019-04-25 |  |  | Issue #43
S2C2122 | Partialy Completed | 2 | Request Call Details Statement from Customer Care | Not fully completed due to the opened issues | 2019-04-18 |  | 1 | #28 #30
S2C2126 | Completed | 1 | Bill on demand |  | 2019-04-12
S2C2130 | Completed | 1 | Cancel Invoice Installment |  | 2019-04-12
S2C2133 | Completed | 2 | Service history details |  | 2019-04-18
S2C2136 | Completed | 1 | Get Installment Templates |  | 2019-04-12
E2R2101 - E2R2102 | Blocked | 3 | Bill Dispute (invoice complaint) | We are not able to get generated invocies, please check issue #43 on bug tracker for more details | 2019-04-25 |  |  | Issue #43
L2S3103 - L2S3104 - L2S3107 | Partialy Completed | 3 | Cash and Invoice Payments in payment step | implemented the logic but still the submission to POS is not completed. Service is not exposed and even if it is we might not be able to provide package id in some cases (this needs discussion in the meeting on Thu 2 May 2019 | 2019-04-24 |  |  | #33
L2S3112 | Completed | 1 | Get All rate plans |  | 2019-04-12
L2S3113 | Completed | 1 | Get allowed services on a rate plan |  | 2019-04-12 |  | 0.5 | #22
L2S3116 - L2S3119 | Partialy Completed | 1 | Create contract on hold and Billing Account | We will do it for telephony. This is not totally completed pending decisions on pending issues | 2019-04-12 |  | 2 | #16 #17 #18 #19 #20 #21 #23 #29 #30
L2S3128 | New | 3 | Get Resources Request in PBX creation
L2S3143 - L2S3146 - L2S3153 - S2C3121 | Completed | 1 | ADSL, GHADSL and Leased Line Contract Activation | Same call in SOM for all contract activations of all LOBs | 2019-04-12
L2S3154 | Blocked | 3 | Add contract to professional Directory Inquiry | It is not clear from CRM side how to implement it. We are checking with Marwan and Ali Younes | 2019-04-23 |  |  | #42
L2S3155 | Blocked | 3 | Remove contract from profressional Directory Inquiry | It is not clear from CRM side how to implement it. We are checking with Marwan and Ali Younes | 2019-04-23 |  |  | #42
L2S3201 | Completed | 2 | Service addition on a contract |  |  |  | 0.5 | #35
S2C3112 | Completed | 3 | Contract Soft Suspension from Dunning |  | 2019-04-19 | 2019-05-04
S2C3112 | Completed | 3 | Contract Suspension from dunning |  | 2019-04-19 | 2019-05-04
S2C3114 | In Progress | 3 | Contract deactivation from dunning |  | 2019-04-19 | 2019-05-04
S2C3115 | Completed | 3 | Revoke Contract soft suspension from dunning |  | 2019-04-26
S2C3116 | Completed | 3 | Revoke Contract suspension from dunning |  | 2019-04-26
S2C3117 | New | 4 | Contract suspension from CRM |  | 2019-04-29
S2C3119 | In Progress | 2 | Activate Pabx service |  | 2019-04-19
S2C3120 | New | 4 | Activate CPT service |  | 2019-04-29
S2C3123 | Completed | 2 | Change Rate Plan |  | 2019-04-18
S2C3124 | New | 4 | Alter ADSL Speed |  | 2019-04-29
S2C3125 | New | 4 | Deactivate wireline contract from CRM |  | 2019-04-29
S2C3128 | In Progress | 4 | Request Directory Number Change from Customer Care | Postman | 2019-04-30
S2C3138 | New | 4 | Micro cells | No idea about it | 2019-04-30
S2C3139 | New | 4 | Change Phone Number Order |  | 2019-04-30
S2C3140 | New | 4 | Contract Take Over |  | 2019-04-16 | 2019-05-02
S2C3144 | New | 2 | Line Move |  | 2019-04-17 | 2019-05-03
S2C3145 | New | 4 | ADSL Line Move Different Switch |  | 2019-04-16 | 2019-05-02
S2C3146 | New | 2 | Line Move Different Switch |  | 2019-04-17 | 2019-05-03
S2C3150 | Completed | 2 | Block Customer from CRM |  | 2019-04-18
S2C3151 | Completed | 2 | Unblock customer from CRM |  | 2019-04-18
S2C3154 | New | 4 | Fulfill Services Add Order for xDSL |  | 2019-04-30
S2C3156 | Completed | 4 | Fuflill Services Add Order for Telephony |  | 2019-04-30

## List of Issues
id | description | category | Severity of the issue | Logging Date | reported by | assigned to | status | last updated by | last updated on | project | organization
35 | L2S3201 - Additional Services to telephony contract | CRM | Critical | 2019-04-19 10:38 | missa | marwan.khoury | New | missa | 2019-04-19 10:38 |  | Ericsson
33 | L2S3103 - Calling POS system | BSCS | Critical | 2019-04-17 16:42 | missa | Akshay | New | missa | 2019-04-17 16:44 |  | Ericsson
32 | S2C2133 - contractServicesReadRequest does not return the full name of the service | BSCS | high | 2019-04-17 13:18 | missa | Akshay | New | Akshay | 2019-04-17 14:27 |  | Ericsson
31 | S2C2122 - calculating number of pages - where to find the price of each page? | CRM | Critical | 2019-04-16 17:41 | missa | marwan.khoury | Assigned | marwan.khoury | 2019-04-17 16:48 |  | Ericsson
30 | L2S3116 - businessTransactionWriteRequest why is needed? | CRM | Critical | 2019-04-16 17:37 | missa | marwan.khoury | Assigned | marwan.khoury | 2019-04-17 16:52 |  | Ericsson
29 | L2S3116 - how to know what service is the SRV Resource | BSCS | Critical | 2019-04-16 12:22 | missa | Akshay | In_Progress | missa | 2019-04-17 13:07 |  | Ericsson
28 | S2C2122 - Request Call Details Statement from Customer Care - Get Bill Cycle | BSCS | Critical | 2019-04-16 10:36 | missa | Akshay | Reopened | missa | 2019-04-18 13:20 |  | Ericsson
27 | S2C2105 - Free Unit and Promotions response is missing | BSCS | Critical | 2019-04-15 17:48 | missa | Akshay | New | Akshay | 2019-04-17 14:51 |  | Ericsson
26 | S2C3150 - S2C3151 - how to block/unblock a contract | BSCS | Critical | 2019-04-15 17:36 | missa | Akshay | ToTest | Akshay | 2019-04-16 15:55 |  | Ericsson
25 | S2C2103 - billingAccountAssignmentReadRequest is needed? | CRM | med | 2019-04-15 15:33 | missa | marwan.khoury | Assigned | marwan.khoury | 2019-04-17 16:55 |  | Ericsson
24 | S2C2105 - Getting line path by contract id is not available | BSCS | high | 2019-04-15 14:21 | missa | Akshay | New | Akshay | 2019-04-17 08:42 |  | Ericsson
23 | L2S3116 - Creating resources for contracts of the different LOBs | BSCS | high | 2019-04-15 14:17 | missa | Akshay | New | Akshay | 2019-04-17 07:47 |  | Ericsson
22 | L2S3113 - Could not succeed to show services that are related to a specific rate plan | BSCS | Critical | 2019-04-15 11:03 | missa | Akshay | ToTest | Akshay | 2019-04-17 08:50 |  | Ericsson
21 | L2S3116 - parameters that are not meaningful for our business are sent static as in the sheet | BSCS | med | 2019-04-15 10:45 | missa | Akshay | Assigned | Akshay | 2019-04-17 13:18 |  | Ericsson
20 | L2S3116 - contractServiceResourcesWrite passing 0 for profile id parameter did not work | BSCS | Critical | 2019-04-15 10:41 | missa | Akshay | ToTest | Akshay | 2019-04-15 16:42 |  | Ericsson
19 | L2S3116 - contractInfoWriteRequest does not exist | BSCS | Critical | 2019-04-15 10:21 | missa | Akshay | ToTest | Akshay | 2019-04-15 12:45 |  | Ericsson
18 | L2S3116 - AddressWrite does not accept contract id | BSCS | Critical | 2019-04-15 10:20 | missa | Akshay | ToTest | Akshay | 2019-04-17 14:55 |  | Ericsson
17 | L2S3116 - contractServiceAdd passing spcode instead spcodePub as parameter | BSCS | Critical | 2019-04-15 09:45 | missa | Akshay | ToTest | Akshay | 2019-04-15 16:38 | ST-CCBS | Ericsson
16 | L2S3116 - genericDirectoryNumberCreateRequest prefix is required | BSCS | Critical | 2019-04-15 09:38 | missa | Akshay | Assigned | Akshay | 2019-04-15 13:04 |  | Ericsson