## Progress
Progress | 42.3077
Total WS | 52
Completed | 17
Partial Complete | 5
Pending | 1
New | 29

## BSCS WS UC
Use Case | SOM Status | Priority | Description | Vanrise Notes | Original Assigned Date | New Planned Date | Delay (days) | Related Issues(ID on bug Tracker)
L2S2101 | Completed | 1 | Create customer (Residential) |  | 2019-04-12
L2S2103 - L2S2108 | Completed | 1 | Update Customer Category |  | 2019-04-12
L2S2104 | Completed | 1 | Update Customer Address |  | 2019-04-12
L2S2105 | Completed | 1 | Update Payment Arrangment of a customer |  | 2019-04-12
L2S2106 | Completed | 1 | Update contract address |  | 2019-04-12
L2S2113 | New | 3 | Add Customer to Directory Inquiry |  | 2019-04-23
L2S2114 | New | 3 | Remove Customer from Directory Inquiry |  | 2019-04-23
S2C2101 | N/A | 3 | Open custome from CTI
S2C2102 | Completed | 1 | Customer read (reading status, balance and customer code) |  | 2019-04-12
S2C2103 | Partialy Completed | 1 | Get Customer contracts (should be done for all LOBs) |  | 2019-04-12 |  |  | #25
S2C2105 | Partialy Completed | 2 | Get contract details |  | 2019-04-18 |  | 1 | #24 #27
S2C2111 | Completed | 1 | Get customer Invoices |  | 2019-04-12
S2C2112 | New | 3 | View Customer Debit/Credit Notes from Customer Care |  | 2019-04-24
S2C2113 - L2S3101 | Completed | 1 | Get Customer payments |  | 2019-04-12
S2C2118 - S2C2121 | New | 3 | Get Invoice Details |  | 2019-04-25
S2C2122 | Partialy Completed | 2 | Request Call Details Statement from Customer Care | Not fully completed due to the opened issues | 2019-04-18 |  | 1 | #28 #30
S2C2126 | Completed | 1 | Bill on demand |  | 2019-04-12
S2C2130 | Completed | 1 | Cancel Invoice Installment |  | 2019-04-12
S2C2133 | Completed | 2 | Service history details |  | 2019-04-18
S2C2136 | Completed | 1 | Get Installment Templates |  | 2019-04-12
E2R2101 - E2R2102 | New | 3 | Bill Dispute (invoice complaint) |  | 2019-04-25
L2S3103 - L2S3104 - L2S3107 | New | 3 | Cash and Invoice Payments in payment step | 103 and 107 are not aligned with the HLD, these use cases need discussions before implementation | 2019-04-24
L2S3112 | Completed | 1 | Get All rate plans |  | 2019-04-12
L2S3113 | Partialy Completed | 1 | Get allowed services on a rate plan |  | 2019-04-12 |  | 0.5 | #22
L2S3116 - L2S3119 | Partialy Completed | 1 | Create contract on hold and Billing Account | We will do it for telephony. This is not totally completed pending decisions on pending issues | 2019-04-12 |  | 2 | #16 #17 #18 #19 #20 #21 #23 #29 #30
L2S3128 | New | 3 | Get Resources Request in PBX creation
L2S3143 - L2S3146 - L2S3153 - S2C3121 | Completed | 1 | ADSL, GHADSL and Leased Line Contract Activation | Same call in SOM for all contract activations of all LOBs | 2019-04-12
L2S3154 | New | 3 | Add contract to professional Directory Inquiry |  | 2019-04-23
L2S3155 | New | 3 | Remove contract from profressional Directory Inquiry |  | 2019-04-23
L2S3201 | Pending | 2 | Service addition on a contract |  |  |  | 0.5 | #35
S2C3112 | New | 3 | Contract Soft Suspension from Dunning |  | 2019-04-19 | 2019-05-04
S2C3112 | New | 3 | Contract Suspension from dunning |  | 2019-04-19 | 2019-05-04
S2C3114 | New | 3 | Contract deactivation from dunning |  | 2019-04-19 | 2019-05-04
S2C3115 | New | 3 | Revoke Contract soft suspension from dunning |  | 2019-04-26
S2C3116 | New | 3 | Revoke Contract suspension from dunning |  | 2019-04-26
S2C3117 | New | 4 | Contract suspension from CRM |  | 2019-04-29
S2C3119 | New | 2 | Activate Pabx service |  | 2019-04-19
S2C3120 | New | 4 | Activate CPT service |  | 2019-04-29
S2C3123 | Completed | 2 | Change Rate Plan |  | 2019-04-18
S2C3124 | New | 4 | Alter ADSL Speed |  | 2019-04-29
S2C3125 | New | 4 | Deactivate wireline contract from CRM |  | 2019-04-29
S2C3128 | New | 4 | Request Directory Number Change from Customer Care | Postman | 2019-04-30
S2C3138 | New | 4 | Micro cells | No idea about it | 2019-04-30
S2C3139 | New | 4 | Change Phone Number Order |  | 2019-04-30
S2C3140 | New | 4 | Contract Take Over |  | 2019-04-16 | 2019-05-02
S2C3144 | New | 2 | Line Move |  | 2019-04-17 | 2019-05-03
S2C3145 | New | 4 | ADSL Line Move Different Switch |  | 2019-04-16 | 2019-05-02
S2C3146 | New | 2 | Line Move Different Switch |  | 2019-04-17 | 2019-05-03
S2C3150 | Completed | 2 | Block Customer from CRM |  | 2019-04-18
S2C3151 | Completed | 2 | Unblock customer from CRM |  | 2019-04-18
S2C3154 | New | 4 | Fulfill Services Add Order for xDSL |  | 2019-04-30
S2C3156 | New | 4 | Fuflill Services Add Order for Telephony |  | 2019-04-30

## List of Issues
id | description | category | Severity of the issue | Logging Date | reported by | assigned to | status | last updated by | last updated on | project | organization
35 | L2S3201 - Additional Services to telephony contract | CRM | Critical | 2019-04-19 10:38 | missa | marwan.khoury | New | missa | 2019-04-19 10:38 |  | Ericsson
33 | L2S3103 - Calling POS system | BSCS | Critical | 2019-04-17 16:42 | missa | Akshay | New | missa | 2019-04-17 16:44 |  | Ericsson
32 | S2C2133 - contractServicesReadRequest does not return the full name of the service | BSCS | high | 2019-04-17 13:18 | missa | Akshay | New | Akshay | 2019-04-17 14:27 |  | Ericsson
31 | S2C2122 - calculating number of pages - where to find the price of each page? | CRM | Critical | 2019-04-16 17:41 | missa | marwan.khoury | Assigned | marwan.khoury | 2019-04-17 16:48 |  | Ericsson
30 | L2S3116 - businessTransactionWriteRequest why is needed? | CRM | Critical | 2019-04-16 17:37 | missa | marwan.khoury | Assigned | marwan.khoury | 2019-04-17 16:52 |  | Ericsson
29 | L2S3116 - how to know what service is the SRV Resource | BSCS | Critical | 2019-04-16 12:22 | missa | Akshay | In_Progress | missa | 2019-04-17 13:07 |  | Ericsson
28 | S2C2122 - Request Call Details Statement from Customer Care - Get Bill Cycle | BSCS | Critical | 2019-04-16 10:36 | missa | Akshay | Reopened | missa | 2019-04-18 13:20 |  | Ericsson
27 | S2C2105 - Free Unit and Promotions response is missing | BSCS | Critical | 2019-04-15 17:48 | missa | Akshay | New | Akshay | 2019-04-17 14:51 |  | Ericsson
26 | S2C3150 - S2C3151 - how to block/unblock a contract | BSCS | Critical | 2019-04-15 17:36 | missa | Akshay | ToTest | Akshay | 2019-04-16 15:55 |  | Ericsson
25 | S2C2103 - billingAccountAssignmentReadRequest is needed? | CRM | med | 2019-04-15 15:33 | missa | marwan.khoury | Assigned | marwan.khoury | 2019-04-17 16:55 |  | Ericsson
24 | S2C2105 - Getting line path by contract id is not available | BSCS | high | 2019-04-15 14:21 | missa | Akshay | New | Akshay | 2019-04-17 08:42 |  | Ericsson
23 | L2S3116 - Creating resources for contracts of the different LOBs | BSCS | high | 2019-04-15 14:17 | missa | Akshay | New | Akshay | 2019-04-17 07:47 |  | Ericsson
22 | L2S3113 - Could not succeed to show services that are related to a specific rate plan | BSCS | Critical | 2019-04-15 11:03 | missa | Akshay | ToTest | Akshay | 2019-04-17 08:50 |  | Ericsson
21 | L2S3116 - parameters that are not meaningful for our business are sent static as in the sheet | BSCS | med | 2019-04-15 10:45 | missa | Akshay | Assigned | Akshay | 2019-04-17 13:18 |  | Ericsson
20 | L2S3116 - contractServiceResourcesWrite passing 0 for profile id parameter did not work | BSCS | Critical | 2019-04-15 10:41 | missa | Akshay | ToTest | Akshay | 2019-04-15 16:42 |  | Ericsson
19 | L2S3116 - contractInfoWriteRequest does not exist | BSCS | Critical | 2019-04-15 10:21 | missa | Akshay | ToTest | Akshay | 2019-04-15 12:45 |  | Ericsson
18 | L2S3116 - AddressWrite does not accept contract id | BSCS | Critical | 2019-04-15 10:20 | missa | Akshay | ToTest | Akshay | 2019-04-17 14:55 |  | Ericsson
17 | L2S3116 - contractServiceAdd passing spcode instead spcodePub as parameter | BSCS | Critical | 2019-04-15 09:45 | missa | Akshay | ToTest | Akshay | 2019-04-15 16:38 | ST-CCBS | Ericsson
16 | L2S3116 - genericDirectoryNumberCreateRequest prefix is required | BSCS | Critical | 2019-04-15 09:38 | missa | Akshay | Assigned | Akshay | 2019-04-15 13:04 |  | Ericsson