## Sheet1
| phases | October | November | December
week 1 | Validation | xDSL validation | Billing/ Accounts Integration validation | Localization validation
Catalog validation
| Requirements confirmation | Billing APIs delivery from Ericsson
| Development | Directory Inquiry | Work Orders | Ticketing
|  | Accounts | EDA | Reporting
|  | Search contacts & requests | Directory Inquiry | Access rights
|  |  | Accounts Integration | Localization
|  |  | Ticketing | Templates
week 2 | Validation | Leased Line validation | CTI validation
|  | Accounts validation | Ticketing validation
Work orders validation
EDA validation
| Requirements confirmation | EDA delivery from Ericsson
CTI
| Development | waiting List | Billing | Localization
|  | xDSL changes | Services consistency | Templates
|  |  | EDA | Resolving bugs
week3 | Validation | waiating list validation
Telephony validation
| Requirements confirmation | Work orders delivery
Ticketing requirmenets discussions
| Development | xDSL | Localization | performance testing
|  | Leased Line | CTI | Resolving bugs
|  | Billing | Work orders
|  | EDA | Access rights
|  | Account Integration | EDA
week 4 | Validation | Directory Inquiry validation | Ticketing validation
|  | Search contacts & requests validation | CTI validation
Service Consistency validation
Access rights validation
| Requirements confirmation | Templates requirements finalization
Catalog
| Development | EDA | reporting | performance testing
|  | Leased line chnages | Localization | Resolving bugs
|  | Accounts Integartion | Accounts Integration
|  | Ticketing | Catalog
Billing
Telephony subscription and operations
Work orders